## Bugs
S/N | Iteration | Date found | Programming task | Bug(s) | Level of impact | Points | Resolved? | Cumulative Points to date | Current unmitigated score | Points | Level of impact
1 | 2 | 2017-09-28 | Data validation | Validation for email testing failed | Low impact | 1 | Yes | 1 | 0 | 1 | Low impact
2 | 3 | 2017-10-04 | Login | Exception thrown during login with invalid username | High impact | 5 | Yes | 6 | 0 | 5 | High impact
3 | 3 | 2017-10-11 | Bootstrap | Couldn’t load data into database when using “load data infile” | High impact | 5 | Yes | 11 | 0 | 10 | Critical impact
4 | 3 | 2017-10-18 | Breakdown | formatDatetime() method in DAOUtility failed | High impact | 5 | Yes | 16 | 0
5 | 3 | 2017-10-18 | Breakdown | Percentage shown in Breakdown report is wrong | Low impact | 1 | Yes | 17 | 0 | Yes | No
6 | 3 | 2017-10-19 | Top K Popular | Number of people shown in Top-k is 0 | High impact | 5 | Yes | 22 | 0
7 | 3 | 2017-10-19 | Top K Popular | Rank shown in Top-k popular place report is ascending | Low impact | 1 | Yes | 23 | 0 | Data validation | Login | Bootstrap | Additional file upload | Breakdown | Top K Popular | Top K Companions | Top K Next | Heatmap | Automatic Group Detection | JSON | UI
8 | 3 | 2017-10-21 | Top K Popular | The same user moved to another semantic places in 15 minute but the counting of the person is in the first semantic place (supposed to be second semantic place) | Low impact | 1 | Yes | 24 | 0
9 | 3 | 2017-10-21 | Additional file upload | Never record error message when verifying duplicates in file | Low impact | 1 | Yes | 25 | 0
10 | 3 | 2017-10-21 | Login | Logout button fails to invalidate session | Low impact | 1 | Yes | 26 | 0
11 | 5 | 2017-11-04 | Login | Login fails with email id | Low impact | 1 | Yes | 27 | 0
12 | 5 | 2017-11-04 | Login | Login successful with whole email address | Low impact | 1 | Yes | 28 | 0
13 | 5 | 2017-11-04 | Bootstrap | Bootstrap error for sample 5. Demographics should show 1670 inserted but shows 1678 | Low impact | 1 | Yes | 29 | 0
14 | 5 | 2017-11-04 | Additional file upload | Removed from database rather than removing from additional file | High impact | 5 | Yes | 34 | 0
15 | 5 | 2017-11-04 | Top K Companions | Going back and forth 2 or 3 times causes error message to display forever even if there should be results | Low impact | 1 | Yes | 35 | 0
16 | 5 | 2017-11-05 | Breakdown | Pie chart for breakdown by school and the text 'breakdown by school appears' when doing breakdown by year during a timeslot with users. When there are no users, just the text 'breakdown by school appears'. | Low impact | 1 | No | 36 | 1
17 | 5 | 2017-11-05 | Breakdown | The text 'breakdown by school appears' when doing breakdown by year whether or not there are users. | Low impact | 1 | No | 37 | 1
18 | 5 | 2017-11-05 | Breakdown | Throws exception | Critical impact | 10 | No | 47 | 10
19 | 5 | 2017-11-05 | Top K Next | Stays on basicLocationReport.jsp, retrieve method from SemanticPlaceDAO returns empty array | Low impact | 1 | No | 48 | 1
20 | 5 | 2017-11-09 | Bootstrap | Fails when bootstrapping a second time | High impact | 5 | Yes | 53 | 0
21 | 5 | 2017-11-09 | JSON | Output is wrong, should be in table form | Low impact | 1 | Yes | 54 | 0
22 | 5 | 2017-11-09 | Top K Popular | Crowd density 0 is missing | Low impact | 1 | Yes | 55 | 0
23 | 5 | 2017-11-09 | Heatmap | Crowd density 0 is missing | Low impact | 1 | Yes | 56 | 0
24 | 5 | 2017-11-09 | Breakdown | Protection missing | Low impact | 1 | Yes | 57 | 0
25 | 5 | 2017-11-09 | UI | Replace logout with back button for Top K Pop | Low impact | 1 | Yes | 58 | 0
26 | 5 | 2017-11-09 | Top K Popular | If same rank should display both, even for rank 2 onwards | Low impact | 1 | No | 59 | 1
27 | 5 | 2017-11-09 | Top K Companions | 0 results - error??? | Low impact | 1 | No | 60 | 1
28 | 5 | 2017-11-09 | Top K Companions | Ranking is wrong, timing also wrong | Low impact | 1 | No | 61 | 1
29 | 5 | 2017-11-09 | Top K Next | Wrong values | Low impact | 1 | No | 62 | 1
30 | 5 | 2017-11-09 | Top K Next | Semantic place naming wrong | Low impact | 1 | No | 63 | 1
31 | 5 | 2017-11-09 | Automatic Group Detection | Should output email and name | Low impact | 1 | Yes | 64 | 0
32 | 5 | 2017-11-09 | UI | Input into seconds should be functional | High impact | 5 | Yes | 69 | 0
33 | 5 | 2017-11-09 | Bootstrap | Input string 101000000 bootstrap fail | High impact | 5 | No | 74 | 5
34 | 5 | 2017-11-09 | JSON | Bootstrap shouldn't have embedded json | Low impact | 1 | Yes | 75 | 0
35 | 5 | 2017-11-09 | Additional file upload | Loaded 0 locations when supposed to have | High impact | 5 | Yes | 80 | 0
36 | 5 | 2017-11-09 | JSON | Additional file has json/json error | Low impact | 1 | Yes | 81 | 0
37 | 5 | 2017-11-09 | Additional file upload | Never print out error messages if locationId has , value | High impact | 5 | Yes | 86 | 0
38 | 5 | 2017-11-09 | JSON | Printing of location and location-lookup were inverted | Low impact | 1 | Yes | 87 | 0
39 | 6 | 2017-11-18 | Bootstrap | Records 0 for location-lookup,csv when there are insertions | High impact | 5 | Yes | 92 | 0
40

## Tasks
Iteration No. | Planned Tasks | Completed Tasks | TM | Action | Score (%) | Action
1 | 5 | 7 | 1.4 | Familiarise ourselves with the routine of regularly updating the schedule | TM < 50 | 1. Immediately inform supervisor about the slip within 24 hours.
2 | 8 | 10 | 1.25 | Schedule longer pair programming sessions for more difficult features like Bootstrapping in the next iteration |  | 2. Use the same mitigation as the category 50 < TM < 90 and seriously consider dropping tasks.
3 | 14 | 17 | 1.2143 | Schedule longer pair programming sessions and more pair programming sessions | 50 < TM <= 90 | 1. Re-estimate the tasks for the future iterations.
4 | 27 | 27 | 1 | Keep it up |  | 2. Deduct the number of days behind schedule from buffer days.
5 | 24 | 24 | 1 | Keep it up |  | 3. If there is no more buffer day, decide the functionalities to drop.
6 | 17 | 19 | 1.1 | Yay | 90 < TM <= 110 | Our estimates are fairly accurate, and we are roughly on track.
1. Add/Deduct the number of days behind schedule from buffer days.
2. If there is no more buffer day, decide the functionalities to drop.
[5 empty] | 110 < TM <= 150 | Grossly over-estimated the effort required.
1. Re-estimate the tasks for the future iterations.
2. Add the number of days gained to buffer days.
[5 empty] | 150 < TM | 1. Immediately inform supervisor about the slip within 24 hours.
2. Use the same mitigation as the category 110 <TM <= 150

## Load Factor
Hours/Day | Planned and actual per iteration
Iteration No. | Planned Hrs | Actual Hrs
1 | 24 | 24
2 | 23.3684 | 23.9416
3 | 16.6411 | 24.6348
4 | 24.2227 | 23.9625
5 | 24.6882 | 23.4292
6 | 26.4134 | 43.7261

## Hours per Member
Hours per member
| JSHK | JSSY | EY | WL | FF
Programming | 92.26 | 103.976 | 83.896 | 97.66 | 99.9
Non-programming | 57.124 | 53.124 | 53.124 | 45.874 | 48.874