## Slide 1: TEAM FOURTRESS
PM REVIEW

## Slide 2: FUNCTIONALITIES
INSERT FUNCTIONALITY WHERE FUNCTION = NONE;
DROP FUNCTIONALITY WHERE FUNCTION = NONE;

## Slide 3: FRAMEWORK
JSP MODEL 2
USAGE OF MODEL-VIEW-CONTROLLER ARCHITECTURE
ITERATIVE TIME-BOXING
INTEGRATION WITH OTHER FUNCTIONALITIES TO BE CARRIED OUT BY THE END OF EVERY ITERATION

## Slide 4: SCHEDULE
WEEK 5- COMPLETE DIAGRAMS AND SCHEDULING
WEEK 6 - COMPLETE LOGIN
WEEK 7 - COMPLETE BOOTSTRAP
WEEK 8 - COMPLETE BASIC LOCATION REPORTS
WEEK 9 - COMPLETE HEATMAP & AUTOMATIC GROUP IDENTIFICATION
WEEK 10 - COMPLETE DUAL INTERFACE
WEEK 11- COMPLETE ALL FUNCTIONALITIES
WEEK 12 – UAT
WEEK 13 – FINAL ADJUSTMENTS
WEEK 14 - FINAL PRESENTATION

## Slide 5: ITERATIONS
6 ITERATIONS
ITERATIVE TIME-BOXING
14 Days (2 Weeks)

## Slide 6: ITERATION 1
INFORMATION GATHERING
  UNDERSTANDING PROJECT REQUIREMENTS
  PLAN PROJECT SCHEDULES
  USE CASE DIAGRAM + LOGICAL DIAGRAM
  PLANNING PROJECT STRUCTURE
WEEK 3 - WEEK 4 (07/09/17 - 21/09/17)

## Slide 7: ITERATION 2
LOGIN & VALIDATION
  CLASS & SEQUENCE DIAGRAM
  UI FOR LOGIN
  VALIDATION LOGIC
  CONNECTION TO MYSQL DATABASE
  START ON BOOTSTRAPPING
WEEK 5 (21/09/2017) - WEEK 6 (05/10/2017)

## Slide 8: ITERATION 3
BLR, BOOTSTRAP & AGI
  PAIR PROGRAMMING
    BASIC LOCATION REPORTS
    BOOTSTRAP
  DISCUSSION ON HEATMAP IMPLEMENTATION
  START ON AGI
  COMPLETE BOOTSTRAP
WEEK 7 (05/10/2017) - WEEK 8 (19/10/2017)

## Slide 9: ITERATION 4
HEATMAP, AGI AND DUAL UI
  COMPLETE HEATMAP
  COMPLETE AGI
  BEGIN DUAL INTERFACE (JSON)
WEEK 9 (19/10/2017) - WEEK 10 (02/11/2017)

## Slide 10: ITERATION 5
WRAPPING UP
  DUAL UI (COMPLETE ALL CSS, JS & JSON)
  FINAL PROJECT INTEGRATION
  RIGOROUS TESTING FOR BUGS
  COMPLETION BY 5 NOVEMBER
WEEK 11 (02/11/2017) - WEEK 12 (16/11/2017)

## Slide 11: ITERATION 6
REFINEMENT
  REVIEWING ON UAT COMMENTS
  IMPROVING OUR SYSTEM BASED ON IT
WEEK 13 (16/11/2017 – 23/11/2017)

## Slide 12: MILESTONES
PM REVIEW (WEEK 7)
APPLICATION DEMO AND PROGRESS UPDATE (WEEK 10)
UAT (WEEK 12)
FINAL PRESENTATION (WEEK 14)

## Slide 13: BUFFER TIME
ITERATION 1
  12/09/2017 - 20/09/2017
ITERATION 2
  29/09/2017 - 4/10/2017
ITERATION 3
  13/10/2017 - 18/10/2017
ITERATION 4
  29/10/2017 - 01/11/2017
ITERATION 5
  10/11/2017 - 15/11/2017

## Slide 14: CRITICAL PATH

## Slide 15: CRITICAL PATH

## Slide 16: CRITICAL PATH

## Slide 17: CRITICAL PATH

## Slide 18: CRITICAL PATH

## Slide 19: CRITICAL PATH

## Slide 20: SCHEDULE METRICS
No Schedule metrics as Team Fourtress is using Time-boxing

## Slide 21: BUG METRICS
Course of action: Immediate debugging during PP
S/N | Iteration | Date found | Programming task | Bug(s) | Level of impact | Points | Resolved? | Cumulative Points to date | Current unmitigated score
1 | 2 | 28/9/2017 | Validation of demographics.csv | Validation for email testing failed | Low impact | 1 | Yes | 1 | 0
2 | 3 | 4/10/2017 | Login | Exception thrown during login with invalid username | High impact | 5 | Yes | 6 | 0

## Slide 22: PP/PM SCHEDULE

## Slide 23: FOURTRESS OUT