## Slide 1: TEAM FOURTRESS
APPLICATION DEMO & PROGRESS UPDATE

## Slide 2: PM REVIEW COMMENTS
Add testing to all critical path (Jorden)
Add testing to project schedule (Feng feng)
Add test cases and test documentation to git (Eugene, Jane)
Create task metrics (Jane)
Remove duplicate minutes (Weiling)
Find the missing git commit in drive (Weiling)
Break down tasks to smaller tasks on Critical path and schedule (Jorden & FF)
Change attended to attendees (Eugene)
Bug metrics (Eugene)
Send email link to google drive (Jane)

## Slide 3: SCHEDULE DURING PM REVIEW
WEEK 7 - COMPLETE BOOTSTRAP
WEEK 8 - COMPLETE BASIC LOCATION REPORTS
WEEK 9 - COMPLETE HEATMAP & AUTOMATIC GROUP IDENTIFICATION
WEEK 10 - COMPLETE DUAL INTERFACE
WEEK 11- COMPLETE ALL FUNCTIONALITIES
WEEK 12 – UAT
WEEK 13 – FINAL ADJUSTMENTS
WEEK 14 - FINAL PRESENTATION

## Slide 4: PROGRAMMING TASKS
BASIC LOCATION REPORT: FENGFENG & JANE
BOOTSTRAP: JORDEN & EUGENE (WEEK 7&8) & WEILING & EUGENE (WEEK 9)
CODE TESTING: WE TEST ON EACH OTHER’S CODE

## Slide 5: NON-PROGRAMMING TASKS
CLASS DIAGRAM: JANE
SEQUENCE DIAGRAM: WEILING & FENGFENG
SCHEDULE: PM OF THE WEEK

## Slide 6: NEW SCHEDULE
WEEK 7 & 8 - COMPLETE BOOTSTRAP & BLR (BREAKDOWN)
WEEK 9 - UPLOAD ADDITIONAL DATA & BLR (TOP-K POPULAR PLACE) & HEATMAP
WEEK 10 - COMPLETE BLR & AUTOMATIC GROUP IDENTIFICATION
WEEK 11 - COMPLETE DUAL INTERFACE
WEEK 12- COMPLETE ALL FUNCTIONALITIES & UAT
WEEK 13 – FINAL ADJUSTMENTS
WEEK 14 - FINAL PRESENTATION

## Slide 7: Updated PP/PM SCHEDULE

## Slide 8: ITERATIONS
6 ITERATIONS
ITERATIVE TIME-BOXING
14 Days (2 Weeks): EXCEPT ITERATION 3 WHICH TOOK 3 WEEKS
ITERATION 4 WILL BE 1 WEEK

## Slide 9: ITERATION 3
BLR & BOOTSTRAP
  PAIR PROGRAMMING
    BASIC LOCATION REPORTS (JANE & FENGFENG)
    BOOTSTRAP (JORDEN & EUGENE/WEILING & EUGENE)
  DISCUSSION ON SCHEDULE & KNOWLEDGE SHARING
  COMPLETE BOOTSTRAP
  BASIC LOCATION REPORTS COMPLETED TWO PARTS
WEEK 7 (05/10/2017) - WEEK 9 (19/10/2017)

## Slide 10: ITERATION 4
HEATMAP, AGI AND CONTINUE ON BASIC LOCATION REPORT
  COMPLETED HEATMAP
  COMPLETE AGI
  COMPLETE BASIC LOCATION REPORT
  DISCUSSION ON SCHEDULE & KNOWLEDGE SHARING
WEEK 9 (22/10/2017) - WEEK 10 (29/11/2017)

## Slide 11: ITERATION 5
DUAL INTERFACE & WRAPPING UP
  DUAL UI (COMPLETE ALL CSS, JS & JSON)
  FINAL PROJECT INTEGRATION
  RIGOROUS TESTING FOR BUGS
  COMPLETION BY 5 NOVEMBER
WEEK 11 (30/10/2017) - WEEK 12 (12/11/2017)

## Slide 12: ITERATION 6
REFINEMENT
  REVIEWING ON UAT COMMENTS
  IMPROVING OUR SYSTEM BASED ON IT
WEEK 13 (13/11/2017 – 19/11/2017)

## Slide 13: MILESTONES
APPLICATION DEMO AND PROGRESS UPDATE (WEEK 10)
UAT (WEEK 12)
FINAL PRESENTATION (WEEK 14)

## Slide 14: TASK METRICS
Iteration No. | Planned Tasks | Completed Tasks | TM
1 | 5 | 7 | 1.4
2 | 8 | 10 | 1.25
3 | 24 | 29 | 1.208333333
4 | 18 | 2 | 0.1111111111
For Iteration 3, total number of tasks = 31 Task metric score is thus a maximum of 129%
Since Task metric is between 110% and 150%:
  Re-estimate the tasks for the future iterations.
  Add the number of days gained to buffer days.

## Slide 15: BUG METRICS
Course of action:
Immediate debugging during PP
If unresolved, schedule unplanned PP to solve bug
S/N | Iteration | Date found | Programming task | Bug(s) | Level of impact | Points | Resolved? | Cumulative Points for Iteration | Current unmitigated score
1 | 2 | 28/9/2017 | Validation of demographics.csv | Validation for email testing failed | Low impact | 1 | Yes | 1 | 0
2 | 3 | 4/10/2017 | Login | Exception thrown during login with invalid username | High impact | 5 | Yes | 5 | 0
3 | 3 | 11/10/2017 | Bootstrap | Couldn’t load data into database when using “load data infile” | High impact | 5 | Yes | 5 | 0
5 | 3 | 21/10/2017 | Additional File | Never record error message when verifying duplicates in file | Low impact | 1 | No | 6 | 0
6 | 3 | 21/10/2017 | Logout | Logout button fails to invalidate session | Low impact | 1 | Yes | 7 | 1

## Slide 16: BUFFER TIME
ITERATION 3  USED ALL BUFFER TIME FOR UNPLANNED PPs
SHOWCASED INACCURATE PLANNING FOR ITERATION 3
REVISED SCHEDULES/ CRITICAL PATHS FOR FUTURE ITERATIONS

## Slide 17: CRITICAL PATH
CRITICAL PATH

## Slide 18
CRITICAL PATH

## Slide 19: CRITICAL PATH

## Slide 20: CRITICAL PATH
CRITICAL PATH

## Slide 21: FOURTRESS OUT